## Project+
Key Word | Book | Page | Summary
project | 1 | 2 | tempory endeaver, definite beginning & ending dates, & results in a unique product/service/result
reason or purpose | 1 | 3 | projects exist for a reason. It's important to document & communicate the purpose & reasons for the project
stakeholder satisfaction | 1 | 3 | a project ends when the goals have been met to the satisfaction of the stakeholders
program | 1 | 3 | group of related projects that are manage together using coordinated processes & techniques
portfolio | 1 | 3 | collections of programs, subportfolios, & projects that support strategic business goals or objectives
operations | 1 | 4 | ongoing & repetative, don't have a beginning or ending date, typically involve ongoing functions
services | 1 | 4 | Ex: providing janitorial services on a contract is operations, providing contract programmers for 18 months is a project
project management | 1 | 4 | brings together a set of tools & techniques to describe, organize, & monitor the work of project activities
project managers | 1 | 4 | people responsible for applying these tools to the various project activites
PM primary purpose | 1 | 4 | integrate all the project components & bring it to a sucessful conclusion
PMBOK | 1 | 4 | A Guide to the Project Management Body of Knowledge (PMBOK Guide) published by the Project Management Institute (PMI)
functional org chart | 1 | 5 | classic setup, staff is organized along department lines with a clear command channel, hierarchical
matrix org chart | 1 | 6 | essentially an employee gets 2 bosses; the department leader and the project manager
strong matrix | 1 | 8 | emphasizes project work over functional duties
weak matrix | 1 | 8 | emphasizes functional work over project work, operates like a functional hierarchy
balanced matrix | 1 | 8 | shares equal emphasis between projects & functional work
projectized org | 1 | 8 | far less common than functional or matrix. The focus is projects rather than functional work units
colocated | 1 | 9 | employees work together at the same physical location
validation | 1 | 12 | A project is validated by preparing a business case & Identifying & analyzing stakeholders.
business case | 1 | 12 | written document or report that helps executive management & key stakeholders determine the benefits of the project
business justification | 1 | 12 | describes the benefits to the org for undertaking the project, can be a section within the business case or a separate document
alignment to strategic plan | 1 | 12 | can also be included in the business case, should describe how the project & its outcomes will align to the org's overall plan
alternate solutions | 1 | 12 | should include high level description of costs, feasibility of emplementing EA alternative, etc
feasibility study | 1 | 12 | determine whether the project is doable & likely to suceed, examine project viability
stakeholder | 1 | 13 | 1:31; anyone who has a vested interest in the project
project sponsor | 1 | 13 | 1:32; executive who authorized the project to begin & has the authority to assign funds & resources to the project
project selection methods | 1 | 13 | used to determine which prooposed projects should receive approval & move forward
decision model | 1 | 13 | formal method of project selection, helps managers make decisions RE use of limited budgets & human resources
benefit measurement | 1 | 14 | first category of decision model, eval using same criteria. Ex: cost-benefit analysis, scoring model, payback period, econ model
cost benefit analysis | 1 | 14 | compares cost of the product/service to the financial gain the org gets from the project
scoring model | 1 | 14 | predefined list of criteria against which EA project is rated. EA criterion is given a scoring range & a weighting factor
payback period | 1 | 15 | cash flow technique that IDs the length of time it takes the org to recover costs of producin the project. Least precise method.
economic model | 1 | 15 | series of financial calculations, aka cash flow techniques, provides data on the overall financials of a project
discounted cash flow | 1 | 15 | compares the value of the future worth of the project's expected cash flows to today's dollars
net present value | 1 | 15 | calculates the revenues or cash flows the org expects to receive over the life of the project in today's dollars
internal rate of return | 1 | 16 | discount rate when the present value of the cash inflows equals the orginal investment
constrained optimization | 1 | 16 | mathematical models, typically used in very complex projects, require a detailed understanding of statistics
expert judgement | 1 | 16 | relies on the expertise of stakeholders, SMEs, or those with previous experience to help reach a decision on project selection
PMK | 1 | 17 | PMBOK Guide term; means Project Management Knowledge Area
10 PMKs | 1 | 17 | Project Integration Management, Scope, Time, Cost, Quality, HR, Communications, Risk, Procurement, Stakeholder
project manager skills | 1 | 18 | leadership, communicating, listening, organization, time management, planning, problem solving, consensus building
leadership | 1 | 18 | understanding how to rally people around a vision & motivate them. Set strategic goals, establish direction, inspire.
communication | 1 | 19 | PMI says project managers spend 90% of their time communicating. It is by far the #1 key to project success.
problem solving | 1 | 19 | Early recognition of the warning sings of trouble will simplify successfully resolving problems with minimal impact.
negotiating | 1 | 20 | process of obtaining mutually acceptable agreements with individuals or groups
MS Sharepoint | 1 | 21 | recommended tool to help organize project documents
customer | 1 | 32 | recipient of the product or service created by a project, also a stakeholder. Aka a client.
champion | 1 | 32 | someone in the org who advocates for the project, typically the project manager or a key stakeholder
project baseline | 1 | 33 | includes approved schedule, cost, scope, & quality plans & documents. Used to measure performance as project progresses
project artifacts | 1 | 34 | documents, templates, agendas, diagrams, & other work products used in managing a project
project coordinator | 1 | 34 | assists the project manager in all aspects, generally in an administrative support function
project scheduler | 1 | 34 | responsible for developing & maintaining the project schedule, communicating timelines/due dates, reporting
project team members | 1 | 34 | experts who will be performing the work associated with the project
PMO | 1 | 35 | Project Management Office; provides guidance to project managers, maintains standards, SOPs, etc RE projects
stakeholder matrix | 1 | 36 | list of stakeholders with info like name, department, phone #, role on project, their level of influence, level of involvement, etc
project request process | 1 | 37 | can be formal or informal, may be a format written doc or it may be a 'drive-by'
drive by | 1 | 37 | project your boss tells you about in the 30 second elevator ride to the lobby [should have taken the stairs]
high level scope | 1 | 37 | describes the project objectives, high level deliverbales, & the reason for the project
process groups | 1 | 50 | Initiating, Planning, Executing, Monitoring & Controlling, Closing
phases | 1 | 50 | CompTIAs term. It means the same thing as PMI's process groups.
initiating processes | 1 | 50 | formal authorization to begin a project, includes project charter, business case/justification, high level scope, ID high level risks
planning processes | 1 | 50 | project goals, objectives, deliverables are broken down into units of work. Time & cost estimates are created.
executing processes | 1 | 52 | where the project's work is done. Deliverables are produced & verified.
monitoring & controlling | 1 | 53 | activities that monitor project progress IOT ID an variances from the plan. Requests for scope changes go here.
closing processes | 1 | 53 | documents the formal acceptance of the project work, hands off the completed product to the org for ongoing support
project charter | 1 | 54 | provides formal approval for the project to begin & authorizes resources applied to the project
project charter cont | 1 | 54 | either the project manager or project requestor writes the project charter. The project's sponsor approves the project charter.
project description | 1 | 55 | 1:70; documents key characteristics of the product/service/end result that will be created by the project.
deliverables | 1 | 55 | measurable outcomes or results that must be produced IOT consider the project complete. Tangible & easily measured.
requirements | 1 | 56 | describe the characteristics of the deliverables that must be met IOT satisfy the needs of the project
milestones | 1 | 56 | 1:104; major events in a project that are used to meausre progress, may also mark completion of key deliverables
high level budget | 1 | 56 | high level estimate of project costs for the project charter, often uses historical info from past projects to estimate costs
assumptions | 1 | 56 | events, actions, concepts, or ideas that you believe to be true and plan for
constraints | 1 | 57 | anything that either restricts or dictates the actions of the project team. Ex: budget, tech, scope, quality, direct orders
triple constraints | 1 | 57 | time, scope, & cost … all of which affect quality
high level risks | 1 | 57 | Include high level risks in the project charter. Risks are potential issues. Constraints are known limitations.
criteria for approval | 1 | 58 | definition of a sucessful project, use to determine whether the final product is acceptable & satisfactory.
formal approval | 1 | 58 | project sponsor should review & sign the project charter, this provides authority to move forward
kickoff meeting | 1 | 58 | 1:136; include the sponsor, key team members, & stakeholders. Have the stakeholders sign the project scope statement!
scope management plan | 1 | 68 | describes how the project team will define project scope, validate the work, & manage/control scope
scope creep | 1 | 69 | involves changing the project or product scope without approval or considering the impact on schedule/budget/resources
change request plan | 1 | 69 | solution to prevent scope creep
scope change | 1 | 69 | inevitable on most projects, the key is handling it within the scope management plan
scope statement | 1 | 69 | includes all the components that make up the product or service of the project & intended results
project objectives | 1 | 70 | describe the overall goal, should be measurable & verifiable, often time-bound
product scope description | 1 | 70 | describes the features, functions, & explains the major characteristics of the product
acceptance criteria | 1 | 71 | processes & criteria used to determine that the dliverables are complete & meet expectations
KPIs | 1 | 71 | 1:245; Key Performance Indicators; help determine if a project is on track & progressing as planned
key deliverables | 1 | 71 | measurable outcomes/results/specific items. Deliverables specified in the scope document must be specific & verifiable.
critical success factors | 1 | 71 | aka deliverables & requirements, those elements that must be completed accurately & on schedule
exclusions from scope | 1 | 71 | anything that is not a deliverable or work of the project. Important to document exclusions from scope.
order-of-magnitude | 1 | 71 | usually wide-ranging estimates, do not have to be precise
influence | 1 | 72 | 1:75; can bring about a constraint or impact an existing constraint
common constraints | 1 | 72 | budget, scope, deliverables, quality, environment, resurces, requirements, scheduling
budget | 1 | 73 | this is always a constraint
scope | 1 | 73 | scope is a constraint because it dictates the actions of the project team in relation to fulfilling the deliverables
deliverables | 1 | 73 | deliverables are constraints because the specific requirements drive [or restrict] the action of the project team
quality | 1 | 73 | is a constraint because ofQA standards
environment | 1 | 74 | weather, rugged conditions, air quality, etc are all potential constraints
resources | 1 | 74 | resources can be a constraint when they are limited, scarce, or not on time
scheduling | 1 | 74 | a constraint on virtually all projects
change request | 1 | 75 | can impact existing constraints or bring new ones
business requirements | 1 | 78 | big picture results of fulfilling a project & how they satisfy business goals, strategy, & perspective
process diagram | 1 | 78 | shows step by step how a process works
functional requirements | 1 | 78 | product characteristics needed for the product to perform. Typically performance or behavior based.
non-functional requirements | 1 | 78 | describe the characteristics of the functional requirements. Not performance or behavior based.
WBS | 1 | 80 | Work Breakdown Structure; deliverables oriented hierarchy that defines all the work of the project
decomposition | 1 | 80 | process of breaking down the high level deliverables into smaller, more manageable work units
work package level | 1 | 81 | lowest level of any WBS, this is where resources/time/cost estimates are dtermined.
code of accounts | 1 | 82 | collection of numeric IDs used for tracking levels of the WBS RE their costs/schedule/resources
WBS dictionary | 1 | 84 | documents the WBS levels & work component descriptions
iterative | 1 | 97 | 1:270; you'll define the scope statement & as they are created more info may come to light, so you'll go back & modify
activity/task list | 1 | 97 | includes every activity needed to complete the work of the project, along with an identifier or code IOT track EA task
sequencing | 1 | 98 | process of identifying dependencies between project activities & sequencing them in proper order
dependencies | 1 | 98 | relationships between activities. One has to finish before another can start.
mandatory dependency | 1 | 98 | directly related to the type of work being performed. Ex: can't lay cable until the trench is dug.
discretionary dependency | 1 | 98 | defined by management, usually process or precedure driven. Ex: process requires approval/sign-off before proceeding
external dependency | 1 | 98 | project task depends on a factor outside the project. Ex: server installation depends on vendor delivering the equipment
internal dependency | 1 | 98 | project task depends on a factor within the project, therefore it's under the control of the project team
predecessor activity | 1 | 99 | one that comes before another activity
successor activity | 1 | 99 | one that comes after the activity in question
logical relationship | 1 | 99 | shows how one activity impacts another
finish-to-start (FS) | 1 | 99 | successor activity cannot begin until the predecessor activity has completed. Most frequently used logical relationship, default.
start-to-finish (SF) | 1 | 99 | predecessor actvity must start before the successor activity can finish. This relationship is seldom used.
finish-to-finish (FF) | 1 | 99 | predecessor activity must finish before the successor activity can finish
start-to-start (SS) | 1 | 99 | predecessor activity must start before the successor activity can start
network diagram | 1 | 99 | depicts the project activities & the interrelationships among these activities
PDM | 1 | 99 | Precedence Diagramming Method; uses boxes to represent project activities & arrows to connect & show dependencies
resource calendar | 1 | 100 | describes the time frames in which resources are available
analogous estimating | 1 | 101 | aka top-down estimating, uses actual durations from similar tasks in prior projects, frequently used in early stages of a project
expert judgement | 1 | 102 | people most familiar with the work determine the estimated duration, ideally the team member who will perform the task
parametric estimating | 1 | 102 | quantitative based estimating method that multiplies the quantity of work by the rate
PERT | 1 | 102 | Program Evaluation & Review Technique; developed by the Navy in the 1950s
expected value | 1 | 102 | (optimistic + pessimistic + (4 x most likely)) / 6
expected value Example | 1 | 102 | (7 + 14 + (4 x 10)) / 6 = 10 days
milestone chart | 1 | 104 | tracks the scheduled dates & actual completion dates for major milestones
gantt chart | 1 | 105 | typically display the tasks using a horizontal bar chart format across a timeline
CPM | 1 | 105 | Critical Path Method; determines the amount of float time for EA activity by calculating earliest & latest start & finish dates
float time | 1 | 105 | amount of time you can delay the earliest start of an activity without delaying the ending of the project
critical path tasks | 1 | 105 | tasks with zero float
critical path | 1 | 106 | longest full path on the project
duration compression | 1 | 107 | used during planning to shorten the planned duration of the project or during execution to help resolve schedule slippage
crashing | 1 | 107 | typically implemented by adding more resources to the eritical path tasks IOT complet the project quicker
fast tracking | 1 | 107 | performing multiple tasks in parallel that were previously scheduled to start sequentially
schedule baseline | 1 | 108 | final/approved version of the project schedule, includes baseline start & finish dates & resource assignments
quality gates | 1 | 108 | used to determine quality checks at strategic points in the project, ensure work is accurate & meets standards
toll gate | 1 | 108 | aka quality gate; from PMI: standardized control point where project status is reviewed & approved [or not] to continue
governance gates | 1 | 109 | used as approval points in the project. Can also be approval checkpoints in large projects.
governance gates cont | 1 | 109 | CompTIA lists 3 governance gates: client sign-off, management approval, & legislative approval
physical resources | 1 | 121 | equipment and materials
dedicated resources | 1 | 121 | project has full control & authority of the resource time & the tasks they work on
shared resources | 1 | 122 | works for both the functional manager & the project manager
low quality resources | 1 | 122 | what functional managers tend to give up for a project. Think employees who are lower skilled or abrasive
resource shortage | 1 | 122
resource overallocation | 1 | 122 | resource needed for the project task is also assigned to other projects
benched resources | 1 | 122 | those who have finished a project and are not yet assigned to a new project (typical in projectized orgs)
interproject dependencies | 1 | 124 | occur when you need the completed deliverables from one project IOT work on the current project
interproject resource contention | 1 | 124 | interproject resource contention is similar to resource overallocation
project org chart | 1 | 125 | similar to a normal org chart
OBS | 1 | 125 | Org Breakdown Structure; chart tha shows the departments, work units, or teams within an org & their work packages
RBS | 1 | 125 | Resource Breakdown Structure; breaks down the project work according to the types of resources needed
RAM | 1 | 126 | Responsibility Assignment Matrix; matrix based chart, maps WBS elements to the required resources
RACI chart | 1 | 126 | shows who is Responsible for doing work, Accountable for the work, Consulted, & Informed
forming | 1 | 127 | beginning stage of team formation, brings team members together & told the project objectives
storming | 1 | 128 | team members are vying for position & control during this stage
norming | 1 | 128 | things calm down, team members know each other and their role. They begin working on project problems.
performing | 1 | 128 | stage where the team is producing & effective. This is the mature development stage.
adjourning | 1 | 128 | refers to breaking up the team after project completion & returning them to their functional managers & teams
team building | 1 | 128 | set of activities or exercises designed to get a diverse group to work together efficiently & effectively
trust building | 1 | 129 | occurs over time, includes doing what you say, supporting the team, showing concern, being humble
performance feedback | 1 | 130 | should be given in a timely manner & objective
training | 1 | 131 | determine the team member's skills/abilities, assess project needs, & provide necessary training
conflict | 1 | 132 | incompatibility of desires/needs/goals between two parties
smoothing | 1 | 133 | temporary way to resolve conflict. Areas of agreement are emphasized over differences, real issue stays buried
forcing | 1 | 133 | permanent conflict resolution technique, but not the best. One person forces a solution on the other parties.
compromising | 1 | 134 | everyone gives up something IOT reach a solution
confronting | 1 | 134 | aka problem-solving, best way to resolve conflict. Involves fact finding to get a solution. Approach used most often.
avoiding | 1 | 134 | aka withdrawel, never results in conflict resolution. Probably the worst technique.
negotiating | 1 | 134 | often used by collective bargaining orgs
analogous estimating2 | 1 | 149 | approximates project cost at a high level by using a similar past project as a basis for the estimate
analogous estimating3 | 1 | 149 | least accurate estimating cost technique, but also the least costly. Used at the early stage of the project
top-down estimating | 1 | 149 | aka analogous estimating or order-of-magnitude
order-of-magnitude | 1 | 149 | aka analogous estimating or top-down
parametric estimating | 1 | 149 | uses the quantity of work x the rate
bottom-up estimating | 1 | 149 | assigns a cost estimate to each work package on the project. Most accurate cost estimate technique, also most time consuming
work effort | 1 | 150 | total time it will take for a person to complete the task if they do nothing else
three-point estimates | 1 | 151 | average of the most likely, optimistic, & the pessimistic estimates. Ex: (120 + 110 + 150) / 3 = $126.67 per hour
cost baseline | 1 | 153 | total expected cost for the project
project budget | 1 | 153 | used to track the actual expenses incurred against the estimates
chart of accounts | 1 | 154 | lists the account # & description for EA category of expense you'll use on the budget
contingency reserve | 1 | 155 | certain amount of $ set aside to cover costs from possible unexpected adverse events
management reserve | 1 | 155 | amount set aside by upper management to cover future situations that cannot be predicted
expenditure tracking | 1 | 156 | measures the project spending to date, determines the burn rate, & tracks expenditures to the cost baseline
burn rate | 1 | 156 | how fast the project is going through the money
expenditure reporting | 1 | 156 | mechanism used to report on the current state of the project budget
EVM | 1 | 157 | Earned Value Measurement; performance measurement technique, compares what project produced to what it cost
planned value (PV) | 1 | 157 | cost of work that has been authorized/budgeted for a specific WBS component during a given time period or phase
actual cost (AC) | 1 | 158 | actual cost of completing the work component in a given time period
Earned Value (EV) | 1 | 158 | value of the work completed to date as it compares to the bedgeted amount (PV) for that period
cost variance (CV) | 1 | 158 | tells whether the costs are higher than budgeted or lower. Formula: CV = EV - AC
scheduled variance (SV) | 1 | 159 | compares an activity's actual progress to date to the estimated progress. Represented in terms of cost.
CPI | 1 | 159 | Cost Performance Index; measures the value of the completed work against the actual cost. Formula: CPI = EV / AC
SPI | 1 | 159 | Schedule Performance Index; measures the progress to date against planned progress. Formula: SPI = EV / PV
ETC | 1 | 160 | 2:55; Estimate To Complete; cost estimate for the remaining project work. Obviously should be < budget - spending so far
S curve | 1 | 161 | project costs displayed graphically over time tend to form an S curve
risk planning | 1 | 161 | ID the potential risks, analyze the potential impact of each, & develop an appropriate response
risk identification | 1 | 162 | process of determining & documenting the potential risks that could occur
risk register | 1 | 163 | essentially a list of risks, includes ID #, risk name, risk description, risk owner, & response plan
SWOT | 1 | 163 | Strengths, Weaknesses, Opportunities, & Threats
SWOT analysis | 1 | 163 | involves analyzing the project from each perspetive
risk analysis | 1 | 163 | process of identifying those risks that have the greatest possiblity of occuring & the greatest impact if they do
probability & impact matrix | 1 | 164 | easy way to prioritize & quantify risks
risk probability | 1 | 164 | likelihood that a risk will occur
risk impact | 1 | 164 | consequence the risk poses to the project if it occurs
risk tolerance | 1 | 165 | make certain you understand the stakeholder's risk tolerance!
risk response planning | 1 | 165 | process of reviewing the risk analysis & determing what, if any, action should be taken IOT reduce negative impacts
risk avoidance | 1 | 166 | avoid the risk altogether by not engaging in the activity
risk transferrence | 1 | 166 | move the liability to a 3rd party by buying insurance
risk mitigation | 1 | 166 | reduce the impact of the risk
risk acceptance | 1 | 166 | choosing to accept the consequences of the risk
exploit | 1 | 166 | looking for opportunities to take advantage of positive impacts
share | 1 | 166 | assigning it to a 3rd party who is best able to bring about an opportunity
enhance | 1 | 166 | monitoring the probability of an event to assure benefits are realized
risk triggers | 1 | 167 | sign or a precursor signaling that a risk event is about to occur
sender | 1 | 180 | person responsible for putting the info together in a clear & concise manner
message | 1 | 180 | info that is being sent & received
receiver | 1 | 180 | person for whom the message is intended
transmitting | 1 | 180 | the way the info gets from the sender to the receiver
decoding | 1 | 180 | what the receiver does with the info once they get it
nodes | 1 | 181 | aka participants in communication
lines of communication | 1 | 181 | (# of participants x (# of participants - 1)) / 2 or n(n - 1) / 2
listening | 1 | 182 | actively engage with the sender & ask clarifying questions
meetings | 1 | 183 | prevalent during projects
virtual meetings | 1 | 184 | simply means that not everyone is physically present
closure meetings | 1 | 184 | important because these are where final acceptance of the project deliverables occurs
communication plan | 1 | 186 | defines who needs what info, types of info needed, communication format, etc
communication triggers | 1 | 194 | bring about the need to update stakeholders
gate reviews | 1 | 195 | occur at predetermined points in the project
project suspension | 1 | 195 | likely in cases of fidasters or incidents
triple constraints cont | 1 | 195 | any change to schedule, budget, or scope is a communication trigger!
triple constraints cont | 1 | 207 | key parts: scope statement, schedule, commo plan, resource plan, procurement plan, budget, QA plan, risk management plan
corrective actions | 1 | 209 | bring the work of the project into alignment with the project management plan
preventive actions | 1 | 209 | implemented to help reduce the probability of a negative risk event
defect repairs | 1 | 209 | either correct or eplace components that are substandard or malfunctioning
change control systems | 1 | 209 | documented procedures for how the project deliverables are controlled, changed, & approved
change request | 1 | 210 | should always be in writing
change request log | 1 | 210 | assign CRs a tracking # and put them in a log
regression plan | 1 | 212 | ability to reverse changes or back out the changes & revert to the previous state
rollback plan | 1 | 212 | go back to the previously known, working state
CCB | 1 | 212 | Change Control Board; reviews CRs & either approves, denies, or defers the request
merger | 1 | 214 | two businesses come together to perform business as one org
acquisition | 1 | 214 | one business takes over another
demerger | 1 | 114 | aka split, opposite of a merger.
business process changes | 1 | 214 | automating a process that previously was performed on paper for example
reorganization | 1 | 215 | can impact available resources
relocation | 1 | 215 | physical move of the org
outsourcing | 1 | 215 | org uses external resources to perform business processes & tasks
procurement planning | 1 | 215 | ID the goods/services required for your project that will be purchases from outside the org
make-or-buy | 1 | 215 | analysis that determines whether it's more cost effective to produce in house or procure something
SOW | 1 | 216 | Statement of Work; details the good/services you want to procure
solicitation | 1 | 217 | process of obtaining responses from vendors IOT complete work as documented in the SOW
RFI | 1 | 217 | Request for Information; used to gather more info on good/services, vendors, & potential cost
RFQ | 1 | 217 | Request for Quote; similar to RFI
RFP | 1 | 217 | Request for Proposal; submitted once ready to procure
bidder conference | 1 | 217 | meeting with prospective vendors prior to their completing the RFP, used to clarify issues with RFP
sole source | 1 | 219 | documentation to support procurement from only one vendor, Cisco for example
contract | 1 | 219 | legal, mutually binding document that describes good/services provided, cost, & penalties for noncompliance
fixed-price contract | 1 | 219 | states a fixed fee/price for the good/services. Used for well defined products with clear/concise SOW
cost-reimbursable contract | 1 | 220 | reimburses the seller for all the allowable costs outlined in the contract.
time/materials contract | 1 | 220 | cross between fixed-cost & cost-reimbursable. The buyer & seller agree on a rate. Often used for staff augmentation.
NDA | 1 | 220 | nondisclosure agreement; used to guard against outside entities sharing confidential info
cease & desist letter | 1 | 220 | legally informs another party to stop something
letter of intent | 1 | 220 | outlines the intent of both parties before entering into a contract
MOU | 1 | 220 | Memorandum of Understanding; like a contract or SLA, but not legally binding
SLA | 1 | 220 | Service Level Agreement; defines service level performance expectations
Purchase Order (PO) | 1 | 220 | describes the specs & quantities being purchased & price. Legally binding once accepted by the seller.
warranty | 1 | 221 | guarantee that the product will meet expectations & perform as stated
agile project management | 1 | 221 | manages in small, incremental portions of work that can completed within a short period
iteration/sprint | 1 | 221 | always time bound, typically 2 weeks
scrum master | 1 | 221 | coordinates the work of the sprint. Is a facilitator, not a manager. The team doesn't report to the scrum master.
product owner | 1 | 221 | represents the stakeholders, is a liaison between them & the scrum master
sprint planning | 1 | 222 | team members choose items from the backlog to work on
backlog | 1 | 222 | list of requirements for the project [in scrum/agile]
user stories | 1 | 222 | aka sprint items in scrum/agile
burn-down chart | 1 | 222 | shows the remaining work effort [or time remaining] for the sprint [in scrum/agile]
daily standups | 1 | 223 | aka scrum meetings, should be at the same time/place daily & no more than about 15 minutes
retrospective meeting | 1 | 223 | after each sprint, determines overall progress, completed work, work for the next sprint, etc
waterfall method | 1 | 224 | each phase is completed in its entirety before moving on to the next phase
PRINCE2 | 1 | 224 | Projects in Controlled Envrironments version 2; incorporates QA, comprehensive methodoly supported by UK government
histogram | 1 | 236 | displays the frequency distributions of variable data
fishbone diagram | 1 | 237 | cause & effect diagram, shows relationships between the effects of problems & their causes
Pareto chart | 1 | 237 | displayed as histograms that rank/order the most important factors by their frequency over time
run chart | 1 | 239 | shows data collected over time as plots on a line, used to catch patterns or trends
scatter diagram | 1 | 239 | plots 2 numerical variables on a chart IOT determine whether there is a correlation
dashboards | 1 | 240 | visually depict the progress of the project
status meetings | 1 | 240 | should occur regularly, provide updated info RE project progress
meeting agenda | 1 | 241 | sent out 1 or 2 days before a meeting, describes the topics
meeting minutes | 1 | 241 | should be distributed to attendees within a day or two & a copy filed in the project documents
issues | 1 | 241 | items that arise that could impact the project
issue log | 1 | 241 | includes ID #s for tracking, date, descriptions, who reported the issue, who owns the issue, action plan, status, closed date
action items | 1 | 242 | tasks that come up, usually at status meetings, that require follow up or resolution
status reports | 1 | 242 | written summary of the project's progress, much more detailed than dashboards
wiki pages | 1 | 244 | typically org internal, useful for project docs, CR docs, & general info
vendor knowledge bases | 1 | 244 | collection of info about a product, kept up to date
collaboration tools | 1 | 244 | Ex: Sharepoint. Allow teams to work on the same doc while maintaining version control
KPPs | 1 | 246 | Key Performance Parameters; similar to KPIs, only they are used to set operational goals/performance levels for systems
balanced score card | 1 | 246 | strategic management tool used to measure the activities/processes a business uses to meet strategic goals
addition [project end] | 1 | 247 | projects that evolve into ongoing operations are considered ended because of addition
starvation | 1 | 248 | resources are cut off from the project or are no longer provided, leaves the project unfinished
integration | 1 | 248 | occurs when the project resources are distributed to other org areas or assigned to other projects
extinction | 1 | 248 | means the project has been completed and accepted by the stakeholders
obtaining sign off | 1 | 249 | primary focus of the closing phase. Org accepts the final product. Sign off should be documented & just a formality.
transfer the product | 1 | 249 | sign-off kicks off the beginning of the warranty period & transfer of the product to maintenance & operations
releasing team members | 1 | 250 | as they finish their work team members are released back to their functional manager
close out contracts | 1 | 250 | completing & settling the terms of the contract & documenting acceptance
administrative closure | 1 | 251 | gathering project docs, perform an AAR, & write the final project close report
archiving project docs | 1 | 251 | important for potential legal requirements & so the docs are available for future projects
lessons learned | 1 | 251 | include key team members, the sponsor, & key stakeholders. The purpose is to conduct a good AAR.
project close report | 1 | 254 | final status report for the project, provide to all stakeholders. Include recap, statement of acceptance, summary of costs, AAR
Pearson Project+ study guide, terms that didn't seem to appear in the Sybex book
supportive PMOs | 2 | 36 | supply projects with access to the project knowledge base & exercise low level project control
controlling PMOs | 2 | 36 | provide the same access but also require compliance with established PMO standards, exercise moderate project control
directive PMOs | 2 | 36 | directly manage all projects & exercise high level project control
total project cost | 2 | 50 | all costs specific to a project incurred from the Initiating phase to the Closing phase
total estimated costs | 2 | 50 | (TEC); all the estimated costs in the initial project budget
other project costs | 2 | 50 | (OPCs); all other project costs that are not included in the Total Estimated Costs
forecasting | 2 | 54 | allows the project manager to predict the project's future based on current performance
EAC | 2 | 54 | Estimate At Completion; calculated when changes have resulted in the need for additional funds
ETC | 2 | 55 | 1:160; Estimate To Complete; approximate idea of how much money will be required to complete the remaining project work
EAC value | 2 | 56 | Estimate At Completion; used once it is apparent that the cost baseline is no longer viable
TCPI using EAC | 2 | 56 | used if cost baseline is no longer viable. Formula is TCPI [using EAC] = (Budget - EV) / (EAC - AC)
TCPI | 2 | 56 | To-Complete Performance Index
TCPI formula | 2 | 56 | TCPI = (Budget - EV) / (Budget - AC) .
reserve analysis | 2 | 57 | method of determining funds that are held to account for any cost uncertainty that the project may encounter
project reserves | 2 | 57 | provisions in the budget to mitigate cost and/or schedule risks
Early Start (ES) | 2 | 74 | earliest start date for EA task. The ES is 0 for the first task in any critical path
Early Finish (EF) | 2 | 74 | earliest finish date for EA task. The EF for the first task in any critical path is the same as the duration
Late Start (LS) | 2 | 74 | subtract the duration from the LF
Late Finish (LF) | 2 | 74 | equal to the LS of the task after it
slack | 2 | 74 | aka float, difference between the LS & ES values for a task, shows how much scheduling leeway a task has
forward pass | 2 | 74 | method used for calculating ES & EF
backward pass | 2 | 75 | start with the last task(s) & calculate LS & LF
preassigned resources | 2 | 90 | personnel assigned to the project from the start based on position and/or knowledge & skill sets
negotiated resources | 2 | 90 | personnel the project manager wants on the project team & must negotiate with other managers to obtain
acquired resources | 2 | 90 | personnel from outside sources, such as consultants & subcontractors
predictive planning | 2 | 111 | uses historical data to provide a linear development plant structured around the desired result
adaptive planning | 2 | 111 | allows a project to evolve as needed to face changing conditions
iterative process | 2 | 111 | makes progress toward the desired result in a sequence of refinements
incremental process | 2 | 111 | produces usable deliverables at EA step of the process
burndown charts | 2 | 115 | common in Agile sprint tracking. Shows the amount of effort expended & remaining for the current sprint.
corporate environment | 2 | 133 | includes the type of org & the org's culture
global environment | 2 | 133 | backdrop that sets the stage for the project, such as regulatory/physical/political/fiscal environment
brainstorming | 2 | 153 | use a facilitators help to obtain a list of project risks
interviewing | 2 | 153 | encourage project team members, stakeholders, & SMEs to ID risks
root cause analysis | 2 | 153 | ID project problems and the causes that led to them, then develop preventive actions
delphi technique | 2 | 153 | develop a risk list based on expert opinion
qualitative risk | 2 | 153 | analysis that prioritizes risk based on their probability & impact
quantitative risk | 2 | 154 | analysis that numerically looks at & catergorizes risk effects on project objectives
risk review | 2 | 155 | periodically investigating risks during the project's Monitoring & Controlling phase to detect any new risks
risk enhancement | 2 | 162 | strategy for positive risks, ID the key risk drivers that affect it & adjust them to increase the probability
risk sharing | 2 | 162 | strategy for positive risks, whereby partial ownership of the risk is allocated to a third party
cognitive constraints | 2 | 183 | cultural world views that provide a backdrop to which all new information is compared. Ex: religion, gender
behavioral constraints | 2 | 183 | behavioral rules for each culture that affect verbal/nonverbal communication. Ex: eye contact
emotional contraints | 2 | 183 | cultural rules for displaying emotion. Ex: yelling, crying, etc
dominant personality | 2 | 188 | aka direct or controlling, require communications to be brief & compelling, just the facts, light on details
influencer personality | 2 | 188 | very social, prefer back & forth, want details, provide a lot of feedback
steadiness personality | 2 | 188 | calm, cool, collected, loyal, thrive on sincere appreciation
cautious personality | 2 | 188 | task oriented, prefer appointments vs impromptu, often want detailed documentation
Terms from the PMI/Google/etc that weren't in either book
critical chain method |  |  | modifies the schedule based upon resource constraints. Takes into account task dependencies, limited resources, & buffers
Ishikawa diagram |  |  | aka Fishbone Diagram; helps determine the root cause of an issue
Precedence Diagramming Method |  |  | uses nodes to symbolize activities and arrows to show how their dependencies are connected
arrow diagramming method |  |  | used to determine the optimal sequencing of events, used for scheduling & to determine the critical path through nodes
resource leveling |  |  | start and finish dates are adjusted based on resource limitation, balances demand for resources with the available supply
requirements document |  |  | written in a natural language, describes the services the product must deliver from a user's perspective
team contract |  |  | agreement between you and your teammates about how your team will operate, a set of conventions that you plan to abide by
Monte Carlo |  |  | risk management technique, quantitative risk analysis, provides a range of possible outcomes & propabilities of EA scenario
project transition plan | 1 | 250 | tasks & activities to efficiently transition the project from the implementation phase to the maintenance phase
project transition plan cont |  |  | aka it is the plan to move something from being a project to being part of daily operations. It would be done in project closing.
integration plan | 1 | 250 | aka project transition plan, moves from a project into daily operations